## Revision History
© 2016 Motorola Solutions Internal Use Only
Title: | D-Stream Checkpoint Requirements
Version | 1.02
Date: | 2016-05-13
Abstract: | This document contains the D-Stream Requirements for each checkpoint to be used as a common standard for maximizing the effectiveness of the D-Stream framework.
Status: | Released
Revision History
Version | Date | Revised By | Ref. # | Description of Revision
1.00 | 2015-06-26 | Debbie Rodriguez | https://converge.motorolasolutions.com/docs/DOC-74954/version/4 | Initial Release
1.01 | 2015-12-03 | Debbie Rodriguez |  | Support for two forms of SAFe (Scaled Agile Framework): Single Release Trains and Continuous Product Line Trains.
1.02-D01 | 2016-04-17 | Debbie Rodriguez |  | Releasing for Comments: Updates for SAFe 4.0: Initiation has been clarified. Single Release Trains are now for Pilots only. Updates to some requirement verbiage for Support Services and IP Strategy Organization to clarify the actions and intent for these organizations. Combined D3.R4 and D3.R5 after feedback from D-Stream users.
1.02 | 2016-05-13 | Debbie Rodriguez | https://docs.google.com/a/motorolasolutions.com/spreadsheets/d/14xq_yzmF2Fx6bmu5UQ7BPm6RF-92VZvvO-NLwHvYRf4/edit?usp=sharing | Final updates after comment period.
Note: If you feel a correction should be made to this document, please submit a question at the D-Stream Converge site.

## D-Stream Checkpoint Reqmts
ID | Requirement | Abstract | Recommended Output / Deliverable / Evidence | Supplier(s) | Approval Level | Mandatory/ Optional | General Notes | Notes for SAFe 4.0 Trains | Notes for Single Release Trains (Pilots)
Initiation | Program Initiation Approval | Owner: Product Management Purpose: This checkpoint represents formal project initiation. It is received from Pipeline Management Level 1 as input to Pipeline Management Level 2, which then charters a Core Team. For SAFe, Portfolio Management or Value Stream Management may approval Initiation of a delivery from a SAFe train or trains. Business Objective: To determine the viability of the proposed program and reject or approve the decision to initiate the project and commit funding resources on the project through D3. | [5 empty] | Initiation applies to the delivery of a release, not the the Train itself. | Initiation does not change
Init.R1 | [Scope] - Prioritized Feature List | Prioritized, high-level feature descriptions (e.g., Customer and Market Requirements) complete. This is the full list of features to be refined to D3 for the Program. | Feature list or features requested for the release in EPP. | Product Mgr | Pipeline Management Team/Portfolio Management or Value Stream Management | M |  | For Initiation of a SW delivery from a SAFe Train, the Initiation (like D3) can be early or late. In an early Initiation, the full scope may not be known, but it may be important for long-lead features or hardware support to be planned for a delivery. It is understood that the full scope will not be known until the last PI before the delivery.
Init.R2 | [Cost] - High Level Costing | The high level costing is based on a short technical description derived from the high-level feature descriptions and contains size, effort, capital, and expense, per functional area. | WAG/ROM level estimates for all features. | System Eng / Architecture | Pipeline Management Team/Portfolio Management or Value Stream Management | M |  | Initiation of a HW Program that will be supported by a SAFe Train requires that the appropriate epic(s) be prioritized into the funnel for the appropriate train(s). This is in addition to the normal Initiation requirement of costing for the hardware program itself.
Init.R3 | [Resources] - Resource Plan | High level resource forecasts to achieve D1. Resource plan to achieve D3. | SPT analysis that validates staffing is available. Named resources to achieve D3. Skill reserves to D1. | Program Mgr/Delivery Mgr | Pipeline Management Team/Portfolio Management or Value Stream Management | M |  | For Initiation of a SW deployment from a SAFe Train, an estimate must be made of the resources that will be needed to support the off ramp. This will be used to determine the capacity for new development during any PIs that overlap the off ramp time frame. Initiation of a HW Program that will be supported by a SAFe Train requires that a decision be made on whether any trains require dial-up of staffing for subsequent PIs in order to meet the desired dates for support of the HW program.
Init.R4 | [Schedule] - D1 Target Date / D3 Review Date | A target timeframe (up to a 3 month window, determined by the Pipeline Management Team/Portfolio Management or Value Stream Management for D1, and a to-the-month date commitment for the D3 Review. | Summary Schedule (including estimates for key program milestones & plan to D3) | Program Mgr/Delivery Mgr | Pipeline Management Team/Portfolio Management or Value Stream Management | M
ID | Requirement | Abstract | Recommended Output / Deliverable / Evidence | Supplier(s) | Approval Level | Mandatory/Optional | General Notes | Notes for SAFe 4.0 Trains | Notes for Single Release Trains (Pilots)
D3 | Commitment | Owner: Program Manager/Delivery Manager D3 is a required checkpoint for Pipeline Management (or Portfolio Management or Value Stream Management for SAFe) approval and cannot be N/A'd without specific business approval. Purpose: To formally commit the organization to the Development phase of the project. The commitment is based on customer requirements, along with an integrated business plan that includes estimates, schedule, resource plans, quality plan, third party statements of work and memorandums of understanding. The commitment process shall include allocations from key stakeholders of funding, staffing, and other resources to ensure the project can be completed in the required timeframe. Business Objective: To commit the feature portfolio, program strategy and resource allocation for a new program and to agree to launch the program(s) required for the solution to develop a specific new system, product or platform. | [5 empty] | For Continuous Product Line Trains: D3 relates to the program/project that is a deployment via the off ramp from a train. The D-Stream checkpoints are on the level of the program/project, not the train. A program is the cost-scope-schedule lockdown for a release. A delivery manager will reference the currently-staffed trains (cost), the currently prioritized feature/epic queues (scope), and the known velocity of the trains, and commit to the schedule for the scope of the program/release. This is based on an assessment of the current state of the active trains and active portfolio layer. No commitment should be made if the forecasts for release date doesn't align with program needs. Then train adjustments are driven by delivery manager (request for dial up on train(s), reprioritization of scope, etc.) A D3 for a deployment from a train can be early or late, depending on the needs of the program/project. An early D3 would provide a commitment to a date for the D2/D1 of the deployment, and visibility to key epics (including new HW supported by the deployment), but not to the entire feature list that will be deployed. A late D3 (typically 1 PI before deployment) would give a clear view of the scope of the deployment as well as to the D2/D1 date. | For Single Release Trains, the program and the train are the same thing. The only real adjustment to D3 is that Portfolio Management or Value Stream Management can choose to commit only key features, and leave bandwidth for other features to be prioritized in later PIs.
D3.R1 | [Resources] - Resource Plan | Resource management plan indicates that all resource pools have sufficient capacity to support the proposed commitment. Named resources are identified for all tasks for a minimum of the next 3 months. | Program or SAFe Train Loading in PDW is sufficient evidence that this requirement has been met. | Engineering Resource Managers, PM | Pipeline Management Team/Portfolio Management or Value Stream Management | M | This will be required for the Pipeline Management Team/Portfolio Management or Value Stream Management approval, and allows team to proceed to Development Phase | Resource plan for the train happens at least once per year per train. Funding to the train can be increased or decreased by the Portfolio Management team. Recommendation is a quarterly review of funding. Estimation of the staffing needed for the "off ramp" is owned by the Project Core Team. Off ramp gets longer or shorter depending on content and maturity of the testing within the PI. Some or all of the resources for the "off ramp" activities may be drawn from the bandwidth of the Train, reducing the velocity of the train while the off ramp activites are ongoing. | No change
D3.R2 | [Cost] - Budgetary Estimates | Budgetary Estimates (BEs) are based on a technical description derived from the baselined feature descriptions. These estimates include Deployment and Capital Expenses, and are reviewed and approved by all impacted resource pool managers and feature owners. |  | Engineering | Pipeline Management Team/Portfolio Management or Value Stream Management | M | This will be required for the Pipeline Management Team/Portfolio Management or Value Stream Management approval, and allows team to proceed to Development Phase | Each set of features gets a refined BE before it is aligned with a product increment. Owned by the train. | BE for at least the first program increment, and any key features that must be committed when D3 occurs. WAGs (Initiation-level) estimates can be used for other features, or bandwidth can be left unassigned to specific features with prioritization happening at each PI. Each set of features gets a refined BE as it is aligned with a program increment.
D3.R3 | [Schedule] - Program Schedule | Milestones/Level 0 schedule to be approved by the Pipeline Management Team (or Portfolio Management or Value Stream Management for SAFe). Detailed schedules for the next phase or minimally the next 90 days (depending on the development model being used) to be reviewed by the Core Team. D2/D1 planned to the month. |  | PM / Engineering | Pipeline Management Team/Portfolio Management or Value Stream Management | M | This will be required for the Pipeline Management Team/Portfolio Management or Value Stream Management approval, and allows team to proceed to Development Phase | Trains commit to PI objectives based on the scope presented to them and their velocity. The Core Team will commit to D2 dates based on their forecasts, and based on the estimate of the staffing/time needed for the off ramp (final box test, SIT testing, etc.). | No change.
D3.R4 | [Scope] - Baselined Feature Descriptions | Baselined feature descriptions (e.g., Customer / Marketing Requirements) complete. In the case of new products, this should also include a services strategy for the product. For unique or complex features, Voice of Customer (VOC) analysis should have been performed to confirm that the proposed solution or marketing requirement meets the customers' needs/expectations. | MRD | Product Mgr | Pipeline Management Team/Portfolio Management or Value Stream Management | M | This will be required for the Pipeline Management Team/Portfolio Management or Value Stream Management approval, and allows team to proceed to Development Phase. The Core Team can agree to waive VOC for small, simple projects or features in well-understood areas. | The Project Core Team commits to key features, and may add to this scope based on what the train has ready when the off ramp starts. While the feature descriptions are clearly used by the trains, the scope of the release is owned by the Project Core Team. | This would only be for the first program increment, and for any key anchor features or customer-committed features.
D3.R5 | Customer Research | Removed (combined with D3.R4)
D3.R6 | Technology, Architecture & Platform Strategy | This requirement ensures that there has been an architecture review conducted by the Architecture Review Board (ARB) to evaluate whether there exists suitable re-use of common platform architecture, software and / or hardware. |  | System Eng | Pipeline Management Team/Portfolio Management or Value Stream Management | O | Optional: May not be needed for small, incremental features that do not impact the architecture. The Architecture process will determine if an ARB is needed. | Per feature Owned by the train. | Per feature
D3.R7 | D3 SC activities are complete. | All Supply Chain (SC) activities defined for D3 have been completed. (http://edoc.mot-solutions.com/ASP/ASPJQ142.ASP?vcodDocumento=44629&vTela=1) |  | Supply Chain Mgr | Functional Teams | M |  | For a SW release for an existing product, needs to be done no later than 1 PI before the off ramp. (At least D2 - 3 Months). New HW products would have their own traditional D-Stream plan. Owned by the Project Core Team. | No change
D3.R8 | EHS Assessment | Evaluate current and near term expected customer and market environmental (green) requirements for the product(s) in the target regions. Environmental Regulatory requirements include energy efficiency performance criteria, specific labels, hazardous substance restrictions, and requirements for free end of life take back. (http://compass.mot-solutions.com/doc/422186569/Revised_2_0_WRS_MGate_Template_EHS(Final)_(3).xlsx) Optional: Not needed for SW only releases |  | Product Mgr | Functional Teams | O | Optional: Required for programs with a hardware component. | Only for new HW Products. Doesn't apply to Software SAFe Trains. | No change
D3.R9 | Quality Plan | Initial quality plan document approved, including aggressive but achievable Quality goals and staffing plans that will drive improvement over prior releases. | SLQAP | Quality | Core Team | M |  | For the program, there will be launch criteria as for any other program. Quality Plan for the Release is owned by the Project Core Team. The quality plan should be focused on the difference between expected quality at the end of an increment and the quality required to deploy to the customer. | No change
D3.R10 | SLPMP for Definition Phase | System Level Program Management Plan (SLPMP) - Initial program management plan document approved. | SLPMP | Program Mgr | Functional Teams | O | Optional: This may consist of links to underlying plan elements, rather than being a stand-alone document. | N/A | N/A
D3.R11 | Initial OSS Plan | Initial Open Source Software (OSS) Plan supplied by Engineering for the OSRB (Open Source Review Board) Representative. |  | Software Engineering | OSRB Rep | O | Optional: Required for programs with a SW component. N/A otherwise. | Updated per increment. Owned by trains. | Updated per increment
D3.R12 | Perform Secure Design Review | Identify any necessary security requirements, which can include changes to existing or proposed feature design, hardening, STIG compliance, operational procedures, etc. Also Identify any follow-up Secure design Reviews that may be necessary | Completion Statement | System Eng | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise. | Evaluation during planning of each PI would be appropriate. If one of the features being prioritized for the PI requires a design review, that becomes a backlog item in the first or second sprint of the PI. Owned by the trains. | Per increment/feature
D3.R13 | Perform Data Privacy and Localization Review | Identify whether this project introduces any new forms of sensitive data. Identify whether the solution architecture transmits, processes, or stores sensitive data in a location other than the customer premises. If the answer to either of the above is "yes" please send an email to privacy1@motorolasolutions.com with the subject "Privacy Assessment" | Completion Statement/Email | System Eng | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise. | Per increment/feature. Owned by the trains. | Per increment/feature
D3.R14 | Plan IA activities | The project plan includes performance of a vulnerability scan at an appropriate time, there is a plan for resolution of issues identified during SDR (or a plan to add them to the roadmap), a plan for applying IA controls, including hardening and patching, a plan for updating and review the IA roadmap, and a plan to complete all IA documentation (C&A documentation, Security Best Practices Guides, etc.) | Milestones in schedule and/or backlog items | Program Mgr/RTE | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise. | Per increment/feature. Owned by the trains. | Per increment/feature
D3.R15 | 3rd Party Supplier Selection and Plan | Conduct Supplier Selection Activities for candidate suppliers identified from the Make vs. Buy process. (Based on High Level Design requirements currently available). These activities include 1) Team identified 2) Supplier Performance Management ensures if an On-Site or Desk-Top Supplier Assessment needs to be conducted for candidate suppliers, 3) If an assessment is required, the appropriate SME's will be engaged to participate, and 4) Presentation of supplier selection results to ISC Management for supplier approval. 5) Service consideration needs to be given to suppliers and their ability to support regionally vs globally. Any agreements should be set up with Services inclusion, requiring signoff from an S&S representative. Ensure Contract has been initiated, and there is a plan to secure final contracts, along with milestones for BOM readiness, test case readiness, and test orders. (NOTE: Supplier selection activities should be followed even if the supplier is sole source or a legacy supplier.) | SOW draft/Strategic Supplier List (http://compass.mot-solutions.com/go/sowsupplierlisttemplate) Plan to secure signed final contract/SOW. Milestones in schedule and/or backlog items for BOM readiness, test case readiness, and test orders. | Product Manager, Category Manager (Procurement) | Pipeline Management Team/Portfolio Management or Value Stream Management | O | Optional: Mandatory if subcontractors are used. N/A if not. Either of the following meets the intent of this requirement: A. Final contracts including any statements of work, subcontractor deliverables and/or payments have been signed and the Strategic Supplier's program support is contractually bound. Third Party Software Audit (3PSA) Matrix is created and includes all the subcontractors under contract. OR B. For long programs or new suppliers, a plan that meets the needs of the program is in place to secure the necessary statements or work, payment schedules, contracts, etc. Third Party Software Audit (3PSA) Matrix is created and includes all the subcontractors planned for the product. In addition to the above, the project schedule should include milestones for confirmation that BOM is "01 status", for approving 3rd party traceability matrix (or reviewing and approving test specs for ODM), and placing (test or customer) MSI orders through the 3rd party factory systems. | A SAFe Train will treat 3rd party deliverables as an activity outside the train, and manage the integration as a backlog item in the appropriate PI. If the Project scope requires the integration of 3rd Party SW, the Project Core Team owns management of this dependency. | No Change (D3)
D3.R16 | SC milestones are planned | The project plan includes milestones for SC activities defined for Ramp Planning and Orderability Readiness (http://edoc.mot-solutions.com/ASP/ASPJQ142.ASP?vcodDocumento=44629&vTela=1). That checklist does not have to be completed at D3. The project plan simply needs to reflect when you will completed it. You can have a single milestone in your project plan for completing the Ramp Planning and Orderability Readiness SC Checklist or multiple milestones for the various items in that checklist. | Milestones in schedule and/or backlog item | Supply Chain Mgr | Functional Teams | M |  | Milestones should be set up during the last PI before entering the off ramp. Owned by the Project Core Team. | No change
D3.R17 | External Team Plans initiated | The PM has notified the following teams of the program, and they have initiated their project plans where needed: Regional Vertical Regional Sales Global Marketing Regional Marketing Web Team Solution Enablement SI Presale SI Engineering and Deployment Support Services Professional Services Global Training Regional Training Lifecycle Services IP Strategy and Operations | Completion Statement | Program Mgr/Delivery Mgr | Core Team | M | Various teams will apply, depending on the scope and specifics of the program. Regional PdM & PIM should be contacted prior to D3 sign off to assess if the region should be in scope, and provide the relevant inputs / requirements. For Support Services, the strategy must be approved by the support team. This means that service offers, and service delivery operations and “flow" has been designed and approved for the products and solutions within the project, including deployment team, technical support, case management, escalations, and on site resources for both early life (beta) and volume deployment. Links: Service Strategy Framework - https://drive.google.com/open?id=1ywwD1O1YgkZouL7ZAytzgAlqY5sflA1yKW_4LS8_I4U Service Strategy Plan (Template) - https://drive.google.com/open?id=18SNRVZTOCWuQuSI6A_51xPFmG2MMkcuztpD3ATaqcUQ For IP Strategy and Operations, furnish the MRD or Initiation slide deck to Jody.Stowell@motorolasolutions.com. The team will receive a determination of which level of participation the IP Strategy and Operations team will use for this project (see D3.R20). | Needs to be done no later than 1 increment before the start of the off ramp. Owned by the Project Core Team. Can use PI demos to help inform/educate stakeholders. | No change
D3.R18 | 3rd Party Commercial Software Audit Initiated | Auditor initiates 3PSA Audit process at D3 (compass.mot-solutions.com/web/rs3psa/Home) | Completion Statement | 3PSA Auditor | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise. | Ongoing and updated per increment. Owned by the trains. | No change
D3.R19 | Business Case | Business case which justifies the project has been completed and reviewed, and the program plan contains periodic revisions and updates to the business case. | Often done as part of the Pipeline Management process prior to D3. | Product Mgr | Pipeline Management Team/Portfolio Management or Value Stream Management | M | Cost and Volume forecast and other required sections should be validated periodically during the program. Going outside of thresholds at any point within the development cycle triggers a mandatory review. | Business case/justification per Epic as it is added to the funnel. Owned by the trains. | No change.
D3.R20 | Intellectual Property Review Plan | The project plan includes at least one Intellectual Property Review. This assessment should take place during development. Depending on the outcome of the initial assessment, D2 Intellectual Property requirements may be N/A. | Milestone in schedule and/or backlog item | Program Mgr/RTE | Functional Teams | O | Level of participation by IP Strategy and Operations (IPSO) will be based on one of the following designations, determined by IPSO in D3.R17: Engaged: IPSO works with the Program Manager/RTE to generate IPR Plan. IPSO actively drives and program manages, organizes scrubs, tracks potential IPR through submission and patent committee review. Monitoring: Limited potential for IPR. No/limited push for IPR, but IPSO will monitor D-Stream activities and track any generated IPR through system to meet deadlines, etc. None: Program Manager/RTE to inform IPSO of any unexpected IPR generated. IPSO to provide guidelines on when to contact. | Part of the IP sprint in each PI. Owned by the trains. | No change
D3.R21 | Subcontractors Plan
D3.R22 | Plan for Customer Introduction Strategy | The project plan includes a milestone for completion of a Customer Touchpoint Plan. The date for this milestone depends on the scope and duration of the project. The Customer Touchpoint Plan will include candidate customers for Customer Touchpoints (Beta, Field, FOA, CI, Demos, etc.) identified to enable test plans to be tailored to the specific configurations of those markets, candidate markets identified for each feature on the release, and criteria required to be met for each type of Customer Touchpoint (demo, alpha, beta, etc.) | Milestone in schedule and/or backlog item | Product Mgr | Core Team | O | Optional: Customer Touchpoints are not required for small, well-understood programs. | Owned by the Project Core Team, but coordinated with the trains and incorporated into Demo plans for each PI. | No change
D3.R23 | Plan for Product/System Test Strategy | The project plan includes a milestone for completion of the Product/System Test Strategy. The date for this milestone depends on the scope and duration of the project. This plan defines test strategy for the various test requirements, such as System Integration and Test, Third Party, Alpha, Beta, FOA, etc. | Milestone in schedule and/or backlog item | SIT / Box Test | Core Team | M |  | One PI before start of an off ramp. Owned by the Project Core Team. | No change
D3.R24 | Plan for Field Test Plan | The project plan includes a milestone for completion of the Field Test Plan. The date for this milestone depends on the scope and duration of the project. The field test plan identifies the expected customer, market and site where the field trial is to take place, the expected configuration of the system, the tests that are expected to be performed and any other information that will assist the Engineering teams to provide an adequate risk assessment of the Field Trial. | Milestone in schedule and/or backlog item | SIT / Box Test | Functional Teams | M | Optional: Field Testing is not required for all programs. | One PI before start of an off ramp. Owned by the Project Core Team. | No change
D3.R25 | Program Commitment Approval | Review held with Pipeline Management Team/Portfolio Management or Value Stream Management and approval received to proceed to D2. | Pipeline Management Team/Portfolio Management or Value Stream Management | Program Mgr/Delivery Mgr | Pipeline Management Team/Portfolio Management or Value Stream Management | M |  | The program D3 can occur as soon as key feature commitments can be made (early binding) or it can happen later when the full scope of the release can be committed (late binding, generally in the PI just preceeding the start of the off ramp. | No change
ID | Requirement | Abstract | Recommended Output / Deliverable / Evidence | Supplier(s) | Approval Level | Mandatory/Optional | General Notes | Notes for SAFe 4.0 Trains | Notes for Single Release Trains (Pilots)
D2 | Production Readiness | Owner: Program Manager/Delivery Manager D2 is a required checkpoint and cannot be N/A'd without specific business approval. Purpose: This is the launch of the commercial product. The expectation is that the product is commercially ready, meets its stated requirements, contains all committed functionality, and is of sufficient quality that the customer can deploy it throughout their network. Business Objective: Product and support systems ready for launch in a commercial environment or network after all product requirements and objectives, as well as administrative and system requirements, have been met | [5 empty] | No change to D2 | No change to D2
D2.R1 | [Resources] - Program Resource Plan for Launch & Close Out Phase | This is the updated resource plan for the organization. It should show that there is sufficient engineering staff committed to this Program to support it through its launch and close-out phase. |  | All impacted organizations | Core Team | O | Optional: Typically not needed for SERs or other small releases if current product MOL plan is sufficient. Escalate if additional resources are needed.
D2.R2 | [Quality] - Product Quality Analysis | Verify the product meets the defined quality criteria. |  | Quality | Core Team | M
D2.R3 | Customer Training | This is the customer training which has been validated in parallel with the product or system. Includes Call Center training. | Customer Training | Cust Train | Functional Teams | M
D2.R4 | Customer Documentation | Customer documentation (including product/system manuals, release notes, etc.) has been validated in parallel with the product or system. | Customer Documentation | Cust Doc | Core Team | M
D2.R5 | Validate New Product Tools and Services Compatibility & Service and Support Plan (SSP) Approved | Service and Account Teams shall validate new product tools and services compatibility, and have tools available and tested for controlled introduction. This may include product support tools, informal or formal tools developed by the account teams and any service offerings that are impacted by the new product introduction. Assure that the Service and Support Strategy has been embraced and that the service stakeholders and critical core team representatives approve the SSP that will be executed on. | Solution Support Plan (Template) | Engineering | Core Team | O | May be waived for SW releases and minor HW changes. An approved Service and Support Plan (SSP) is required for all new products. Tools may not be required if the project does not use fixtures and service equipment.
D2.R6 | Hardware Availability | There should be 1) sufficient material availability to support the build forecast / ramp requirements; and 2) sufficient capacity to support build demand |  | Supply Chain Mgr | Core Team | O | Optional: Required if the program has a hardware component. N/A otherwise.
D2.R7 | Product Launch Readiness | All Product Management / Marketing product launch deliverables (e.g., System Configuration Guide, Marketing Communication Vehicles, Order Entry System, etc.) complete. | BOMs / Designs should be under configuration control such that material can be driven from the supply chain. Lead times should drive when the BOM lockdown / material sourcing plan | Product Mgr | Core Team | M
D2.R8 | Intellectual Property Review | Any patent opportunities identified during the Program, and any trademark or copyright claims and unique manufacturing processes are suitably protected prior to release of the product to the field which constitutes publication of the IPR. |  | Engineering System Eng Supply Chain Mgr | Functional Teams | O | Optional: May be N/A depending on the assessment planned at D3.R17 and D3.R20.
D2.R9 | Product Introduction Planning Complete | Detailed plans for all customers and markets to receive the product/system. |  | Product Mgr | Functional Teams | M
D2.R10 | 3PSA D2 Audit Complete | Auditor performs 3PSA Audit at D2 (compass.mot-solutions.com/web/rs3psa/Home) |  | 3PSA Auditor | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise.
D2.R11 | Final Vulnerability Scan | Run regression scan of all boxes in scope. | Completion Statement | IA Lead | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise.
D2.R12 | Risk Owner Review | Summarize and review all IA artifacts with the Risk Owner. | Updated residual risks in the release | IA Lead | Functional Teams | O | Optional: Required for programs with a SW component. N/A otherwise.
D2.R13 | D2 SA activities complete | All SA activities defined for D2 have been completed. (https://converge.motorolasolutions.com/docs/DOC-90566) | Completed D2 Ship Acceptance Checklist and Cover Sheet | Quality | Core Team | M
D2.R14 | Supply Chain (SC) D2 activities complete | All SC activities defined for D2 have been completed. (http://edoc.mot-solutions.com/ASP/ASPJQ142.ASP?vcodDocumento=44629&vTela=1) | Completed D2 SC Checklist | Supply Chain Mgr | Functional Teams | M
D2.R15 | Business Case Updated | Contains a comparison of plan vs. actual cost and a forecast/update of the business case. |  | PdM | Core Team | O | Optional: Update PFAM, volume forecast, etc. and other required sections. If within plan thresholds, then N/A. Going outside of thresholds at any point within the development cycle, triggers a mandatory review.
D2.R16 | Product System Readiness | Review held with Core Team and approval received to pursue regional ship acceptance (SA). | Core Team Approval | Program Mgr/Delivery Mgr | Core Team | M
ID | Requirement | Abstract | Recommended Output / Deliverable / Evidence | Supplier(s) | Approval Level | Mandatory/Optional | General Notes | Notes for SAFe 4.0 Trains | Notes for Single Release Trains (Pilots)
D1 | Field Readiness | Owner: Program Manager/Delivery Manager for first D1. Subsequent Regional D1s are owned by the Product Manager. Purpose: Marks the point where any customer can order the product in a given region. After this checkpoint, ownership is transferred to the appropriate regional support and account teams. This checkpoint also confirms that the receiving organizations are fully prepared to take over ownership: that they are trained, that their systems (order entry, trouble ticketing, etc.) are updated and that any deployment tools are ready. Business Objective: Permit deployment to the marketplace and verify that development, manufacturing, distribution, marketing, customer support, and sales resources are ready for volume deployment in applicable regions. | [5 empty] | No change to D1 | No change to D1
D1.R1 | [Quality] - Product Quality Analysis | Verify the product meets the defined quality criteria. | Product Quality Analysis | Quality | Functional Teams | O | Optional: Only for additional regions subsequent to the initial launch region. Otherwise, covered by D2.R2.
D1.R2 | Customer Training | This is the customer training for all required languages which has been validated in parallel with the product or system. | Customer Training | Cust Train | Functional Teams | O | Optional: Only for additional regions subsequent to the initial launch region. Otherwise, covered by D2.R3
D1.R3 | Customer Documentation | This is the customer documentation for all required languages which has been validated. | Customer Documentation | Cust Doc | Functional Teams | O | Optional: Only for additional regions subsequent to the initial launch region. Otherwise, covered by D2.R4.
D1.R4 | Customer Support Center, Field, and Delivery Teams Ready | Preparation for, and communication to, After Market Support, Customer/ System Support Center, Field Teams, FSO, and Integration Teams for appropriate staffing, training and inventory management to support the Volume Deployment Plan. | Service Readiness Checklist | Cust Supp Cent | Functional Teams | M
D1.R5 | Hardware Availability | There should be sufficient hardware (seed stock) on site and/or in the supply chain to support the demands of the controlled introduction. |  | Supply Chain Mgr | Functional Teams | O | Optional: Only required for hardware releases, and then only if the business requires seed stock in a distribution center. Otherwise, covered by D2.R6.
D1.R6 | D1 SA activities complete | All SA activities defined for D1 have been completed. (http://compass.mot-solutions.com/go/389551010) | Completion Statement | Quality | Functional Teams | M
D1.R7 | D1 SC activities complete | All SC activities defined for D1 have been completed. (http://edoc.mot-solutions.com/ASP/ASPJQ142.ASP?vcodDocumento=44629&vTela=1) | Completion Statement | Supply Chain Mgr | Functional Teams | M
D1.R8 | Product/System - Regional Ship Acceptance | All Regional Ship Acceptance requirements have been met for all required regions. | SA Approval | Deployment Team Engineering Program Mgr/Delivery Mgr | Core Team | M | First D1 would be handled concurrently with D2 for many programs if seed stock is not needed at a distribution center. At first D1, define the minimum subset of Core Team members that need to review subsequent D1s for new regions.
ID | Requirement | Abstract | Recommended Output / Deliverable / Evidence | Supplier(s) | Approval Level | Mandatory/Optional | General Notes | Notes for SAFe 4.0 Trains | Notes for Single Release Trains (Pilots)
D0 | End of Life | Owner: Retirement Manager Purpose: Represents final product closeout (whereas D1 represented project closeout). It is basically a check that all of the necessary steps to complete the retirement of the product have been executed. Business Objective: Terminate support for the product or system. | [5 empty] | No change to D0 | No change to D0
D0.R1 | Product/System Cancellation Planning | Create business case supporting the need for cancellation. Define cancellation scope. Identify resources required. Define the schedule of activities. Identify and customer contracts that require long term support beyond planned service/support terms. | 1) Contract Book or Business Case for cancellation 2) Cancellation scope definition 3) Named resources and roles/functions 4) Identification of any long term contract commitments | PdM/Contracts Team | Core Team | M | Core Team is Lifecycle Management Team at D0
D0.R2 | Product/System Cancellation Implementation | Identify all orderable models/options/FRUs. Create, review and distribute the Intent to Cancel Memo. Generate and review the Unique Parts List based on all orderable items. Analyze repair usage history from all sites. Identify LTB parts and notify team. Decide on LTB and Execute. Final order date for customers occurs. | 1) List of all orderable models/options/FRUs 2) Intent to Cancel memo/communications 3) Unique parts list and LTB parts 4) Repair usage history report | PdM/Material Planning/Lifecycle Management Team/Customer Fulfillment Center/Manufacturing | Core Team | M | Core Team is Lifecycle Management Team at D0
D0.R3 | Product/System Cancellation Close Out | Clean up demand in MRP. Submit a request to implement holds to prevent orders from being placed. Updated ordering price pages so field can no longer view items as orderable and verify across all regions. Finalize all material and close down production. Close all purchase orders. Status Change Notice Creation for PDM. Scrap remaining parts material. Send Unique Parts List to procurement for supply base rationalization and take supplier out of database. Transfer sourcing to remove MFG site and replace with CFC site and transfer APC ownership to Service when appropriate. Publish list of unique equipment to CFC. Transfer to 3rd party repair site if required. Conduct Lessons learned at project closeout. | 1) Order Hold Requests 2) Ordering price pages updated so items no longer orderable 3) Status Change Notice for PDM 4) Unique Parts List supplied to procurement 5) Lesson Learned | PdM/Material Planning/Lifecycle Management Team/Customer Fulfillment Center/Purchasing/Manufacturing | Core Team | M | Core Team is Lifecycle Management Team at D0
D0.R4 | Product/System Retired | The Product Cancellation (Retirement) Plan has been executed to completion and validated for the product/system. |  | Product Mgr | Cust Supp Cent Deployment Team | M
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?
?